## Slide 1
UPDATES ON BAYANIHAN II PROJECTS
(TEMPORARY TREATMENT & MONITORING FACILITY &
COVID LABORATORY)
June 22, 2021

## Slide 2
TEMPORARY TREATMENT & MONITORING FACILITY
(TTMF)

## Slide 3
Recipient | Location | Infrastructure Cost | Bed Capacity | Implemen ting Agency | STATUS As of June 22, 2021 | REMARKS
Province of Oriental Mindoro | Oriental Mindoro Provincial Hospital Compound, Calapan City | 10,000,000.00 | 18 | PLGU | Under Procurement (For Issuance of Notice to Proceed) | Opening of Bids: June 11, 2021 Notice of Award: June 17, 2021 Contract Agreement: June 22, 2021 Contract Duration: 86 C.D. Target Date of Completion: August 31, 2021
2020 Projects
Bayanihan II Fund – Temporary Treatment and Monitoring Facility

## Slide 4
Recipient | Location | Infrastructure Cost | Bed Capacity | Implemen ting Agency | STATUS As of June 22, 2021 | REMARKS
Province of Occidental Mindoro | Occidental Mindoro Provincial Hospital Compound, Mamburao | 10,000,000.00 | 18 | PLGU | Ongoing | Phase 1 Contractor: AMM Construction & Construction Supplies Contract Amount: P 9,988,140.00 Notice of Award: June 2, 2021 Duration: 300 CD Completion Date as per Contract: April 2, 2022 Target Completion Date of Contractor: August 31, 2021
2020 Projects
Bayanihan II Fund – Temporary Treatment and Monitoring Facility

## Slide 5
Recipient | Location | Infrastructure Cost | Bed Capacity | Implemen ting Agency | STATUS As of June 22, 2021 | REMARKS
Province of Marinduque | Second Floor, Bldg. D., Marinduque Provincial Hospital, Boac | 10,000,000.00 | 17 | PLGU | Ongoing 41.51% | Contractor: T.N.G. Construction Corporation Contract Amount: P 9,988,680.20 Notice of Award: May 3, 2021 Notice to Proceed: May 11, 2021 Duration: 65 CD Target Completion Date: July 15, 2021
2020 Projects
Bayanihan II Fund – Temporary Treatment and Monitoring Facility

## Slide 6
Recipient | Location | Infrastructure Cost | Bed Capacity | Implementing Agency | STATUS As of June 15, 2021 | REMARKS
Province of Romblon | Romblon Provincial Capitol Compound, Romblon | 10,000,000.00 | 36 | PLGU | Ongoing 37.00% | Phase 1 Contractor: Mt. Guiting-GuitingConstruction Contract Amount: P 9,970,814.70 Notice of Award: April 22, 2021 Notice to Proceed: June 2, 2021 Duration: 90 CD Target Completion Date: August 31, 2021
2020 Projects
Bayanihan II Fund – Temporary Treatment and Monitoring Facility

## Slide 7
Recipient | Location | Infrastructure Cost | Bed Capacity | Implementing Agency | STATUS As of June 15, 2021 | REMARKS
Province of Palawan | Second Floor, Southern Palawan Provincial Hospital, Brookespoint | 10,000,000.00 | 27 | PLGU | Ongoing 40.00% reported by PGP | Contractor: Mamsar Construction and Industrial Corporation Target Completion Date: August 31, 2021
2020 Projects
Bayanihan II Fund – Temporary Treatment and Monitoring Facility

## Slide 8
COVID-19 MOLECULAR LABORATORY WITH MEDICAL EQUIPMENT

## Slide 9
Recipient | Location | Infrastructure Cost | Equipment Cost | Implementing Agency | STATUS As of June 22, 2021 | REMARKS
Oriental Mindoro Southern District Hospital | Oriental Mindoro Southern District Hospital Compound, Roxas | P 5,000,000.00 | P 5,000,000.00 | PLGU | Ongoing 5.00% | Infrastructure: Contractor: Marcphil Construction Notice of Award: June 17, 2021 Contract Agreement: June 22, 2021 Contract Duration: 86 C.D. Target Date of Completion based on Calendar Days: September 18, 2021 Equipment: Under PR
2020 Projects
Bayanihan II Fund – Covid-19 Molecular Laboratory with Medical Equipment

## Slide 10
Recipient | Location | Infrastructure Cost | Equipment Cost | Implementing Agency | STATUS As of June 22, 2021 | REMARKS
El Nido Community Hospital | El Nido Community Hospital Compound, El Nido | P 6,000,000.00 | P 5,000,000.00 | PLGU | Ongoing 53.00% reported by PGP | Infrastructure: Contractor: SMMLEY Builders & Trading Contract Amount: P 5,999,488.41 Target Completion Date: August 31, 2021 Equipment: Opening of Bids: June 30, 2021
2020 Projects
Bayanihan II Fund – Covid-19 Molecular Laboratory with Medical Equipment

## Slide 11
Recipient | Location | Infrastructure Cost | Equipment Cost | Implementing Agency | STATUS As of June 22, 2021 | REMARKS
Coron District Hospital | Coron District Hospital Compound, Coron | P 5,000,000.00 | P 5,000,000.00 | PLGU | Ongoing 40.00% reported by PGP | Infrastructure: Contractor: RD Abacial Contract Amount: P 4,989,044.91 Target Completion Date: August 31, 2021 Equipment: Opening of Bids: June 30, 2021
2020 Projects
Bayanihan II Fund – Covid-19 Molecular Laboratory with Medical Equipment

## Slide 12
Thank you.