## Sheet2
Department of Enviroment and Natural Resources
Office of the Secretary (DENR-OSEC)
Visayas Avenue, Quezon City
AGENCY ACTION PLAN and
STATUS of IMPLEMENTATION
Audit Observations and Recommendations
For the Calendar Year 2020
As of __________
Number | Audit Observations | Audit Recommendations | Agency Action Plan |  |  |  | Status of Implementation | Reason for Partial/Delay/Non-Implementation of action, if applicable | Action Taken/Action to be Taken
|  |  | Action Plan | Person/ Dept. Responsible | Target Implementation Date
[5 empty] | From | To
Observation No. 1 | Unadjusted/uncorrected accounting errors/omissions and accounting deficiencies
| We do not express an opinion on the Financial Statements (FSs) due to uncorrected misstatements in aggregate amount of ₱1,216.924 million, which exceeded the materiality level of ₱306.964 million, and various accounting deficiencies such as non-maintenance of Subsidiary Ledgers and lack of complete accounting records on various FS accounts with an aggregate amount of ₱13,310.877 million, which prevented alternative audit procedures to be undertaken to obtain sufficient and appropriate evidence to prove the management's assertions on the accounts, where the possible effect could be material and pervasive. | We reiterated our prior year's recommendations and DENR Management agreed to require the Chief Accountants of the Central and Regional Offices and the Accountants of the PENROs to:
a. effect the necessary adjsutments on the errors/omissions to correct the balances of the affected accounts in the FS;
b. reconcile the variances between the SLCs and RPCI for inventory accounts; PPELCs and RPCPPE for PPE accounts; SLs for all Inter-Agency/ Intra-Agency/Other Receivables, Accounts Payable/Inter-Agency/ Intra-Agency/ Other Payable accounts with the ageing schedules and confimation results; and the Financial Accountability Report with the Notes to FS;
c. trace the details of the dormant accounts/beginning balances and those SLs with negative balances, and prepare adjusting entries, if necessary;
d. maintain complete and updated accounting records, specifically:
i. Supplies Ledger Cards (SLCs) on each type of Inventories;
ii. PPE Ledger Cards (PPELCs) on each category of Property Plant and Equipment including Constrction in Progress Accounts;
iii. Subsidiary Ledgers (SLs) for Receivables, Payables, Income and Accumulated Surplus/Deficit accounts; and
e. ensure that the systems and procedures prescribed for by the GAM for NGAs are observed in the processing and recording of the transactions in the books of accounts in all offices of the DENR, and strengthen the internal control systems in whole of the Department to achieve reliability and fair presentation of the combined financial statements.
Observation no. 2 | Overall Fund Utilization
| Overall, the department's fund utilization of ₱15,959.601 million is 91.07 percent compared to its appropriation/allotment of ₱17,525.277 million, leaving an overall balance of ₱1,565.676 million at year-end due to the non-implementation of some of the agency's programs, projects and activities during the year in view of the various community quarantines measures that the government imposed. | We recommended and the Management of DENR agreed to:
a. cause the full utilization of unobligated allotments for CY 2020 PPAs, which are not yet implemented to realize optimum results and benefits on their completion as timely as intended.
b. direct the officials responsible for the implementation of programs and projects of the MBRP, ENGP, PRCMO and the two Foreign-Assisted Projects (FAPs) FMP and INREMP to ensure the timely implementation of the programs and projects to avoid non-utilization of allotments released for the above-mentioned programs/projects.
Observation no. 3 | Cash utilization/disbursements
| Of the ₱18,024.157 million Notice of Cash Allocations (NCAs) received, inclusive of the two major projects, the ENGP and MBRP, the PRCMO and the two Foreign-Assisted Projects, FMP and INREMP, ₱16,898.037 million or 93.75 percent were utilized inclusive of payment of Accounts Payable, leaving an overall untulized NCAs of ₱1,216.119 million or 6.25 percent. Moreover, cash utilizations were low in DENR-CO, Regions IV-B and XI and PENROs Ilocos Sur and La Union. | We recommend and Management agreed to direct the Regional Executive Directors/PENR Officers of:
a. Regions IV-B and XI to henceforth maximize the utilization of NCAs released to their respective Regional Offices to:
i. closely supervise and monitor the work of the divisions charged with the implementation of the various activities of the Agency for a timely implementation of the P/A/Ps, as well as the Cashier, Budget and Accounting Sections as the administrative support to operations; and
ii. Consider the future impact of the imposition of any community quarantine in the subsequent year's budget through a realistic estimation and to align the Monthly Cash Program with the new budget estimates to come up with a more realistic forecasting and expenditures programming for an efficient management of the monthly cash allocation.
b. PENROs Ilocos Sur and La Union to implement the activities, programs and projects as planned to ensure full and timely utilization of cash allocation for its intended purpose and to ensure the delivery of services to beneficiaries in a timely manner.
Observation no. 4 | Non-reversion of dormant cash, unauthorized accounts and unnecessary fund and non-enforcement of regulations on the use of foreshore lands
| The DENR FAPs, two Bureaus, eight ROs and 51 PENROs have no dormant cash, unauthorized accounts and unnecessary bank accounts for reversion to the National Treasury. However, the FMB, three ROs and six PENROs did not revert its dormant cash, unauthorized accounts, unnecessary special and trust funds amounting to ₱23.623 million as of year-end, contrary to Permanent Committee Joint Circular No. 4-2012, dated September 11, 2012, implementing EO No. 431, dated May 30, 2005. Thus, the government was deprived of the available funds that could be used in its priority programs and projects. | We recommended and Management agreed to require the FMB Bureau Director, Regional Executive Directors of CAR, ROs XII and XIII and six PENR Officers concerned to:
a. close the dormant and/or unauthorized bank accounts and remit the balances, if any, to the Bureau of Treasury (BTr);
b. revert the account to the general fund and correspondingly deposit the dormant/inactive/unauthorized cash balances to the BTr. In case of trust receipts, deposit the funds with the BTr under the Ageny/Treasury Deposit - Trust; and
c. send confirmation letter to the respective Authorized Government Depository Banks (AGDB) of RO XII and PENRO Cebu to confirm the balance and trace the existence or history of bank accounts in the agency records, and deposit all existing account balances to the BTr.
Observation no. 5 | Non-enforcement of regulations on the use of foreshore lands
| Assessed revenues from the use/occupation of foreshore lands amounting to ₱35.123 million were not realized due to lack of collection enforcement and lapses in monitoring the collection efforts by the responsible officials, delayed appraisal of foreshore lease areas, and the absence of approved foreshore lease agreement (FLA), thus, deprived the government of the opportunity to collect such income, which can be used to fund the government's priority programs and projects. | We recommended and Management agreed to direct the Regional Executive Directors and PENR Officers concerned of:
a. the six PENROs to sustain their efforts/strategies to:
i. optimize collections from foreshore lease and occupation fees such as sending bills and demand letters monthly/ regularly; and
ii. develop effective strategies/mechanism/processes for an effective monitoring to ensure enforcement of DENR AO 2004-24 dated August 24, 2004 and other existing laws and guidelines on the use of foreshore lands;
b. PENROs Capiz and Misamis Occidental to facilitate the approval of the Foreshore Lease Agreement; and
c. PENRO Davao Oriental and Davao de Oro to intensify the conduct of inventory/survey of foreshore lands to facilitate processing of pending FLAs and identify unauthorized occupants/settlers.
Observation no. 6 | Non-liquidation of cash advances
| Cash advances during the year for payroll, operating expenses, official local and foreign travels and special purpose/time-bound undertakings amounting to ₱129.721 million in two staff bureaus, ten ROs, and 41 PENROs were liquidated in accordance with COA Circular No.97-002. However, cash advances amounting to ₱27.770 million or 8.96 percent of the cash advances granted during the year of ₱309.757 million were not liquidated in the DENR-CO, FAPs, two staff bureaus, three ROs and 15 PENROs at year-end. Also, there were still unliquidated cash advances in prior years amounting to ₱6.573 million or 19.63 percent of prior year's balance of ₱33.488 million, thus, exposes government funds to possible misuse. | We recommended and Management agreed to:
a. direct the Accounting Units to:
i. refraing from processing additional cash advance of accountable officers with outstanding cash advance/s;
ii. Validate the propriety of the long outstanding balances and request for write off for those balances existing for over ten years; and
iii. Establish the breakdown of the Prior Year Cash Advances to Officer and Employees that are recorded in the books in the lump sum amount.
b. stop the practice of transferring of cash advances from one officer to another who are neither bonded nor designated to act as disbursing officers;
c. strictly enforce the period of liquidation of CA within prescribed period by requiring the accountable officers to immediately liquidate their cash advances as soon as the purpose for which it was granted has already been served;
d. demand from the accountable officers the immediate liquidation of the unliquidated balances of cash advances and the immediate refund/return of any excess amount thereof.
Observation no. 7 | Non-liquidation of fund transfers to Implementing Agencies (IAs) and NGOs/POs
| Fund transfers to NGAs, LGUs, GOCCs and NGOs/POs for the implementation of agency's projects amounting to ₱252.896 million or 69.37 percent of the funds transferred during the year amounting to ₱364.571 million were not liquidated, contrary to Circular No. 94-013 and COA Circular No. 2007-001. Also, there were still unliquidated fund transfers in prior years amounting to ₱2.411 billion or 87 percent of prior year's balance of ₱2.772 million. | We recommended and Management agreed to direct te Chief Accountants of DENR-CO and ROs and the Accountants of Bureaus and PENROs to:
a. closely monitor the implementation of projects and the status of fund transfers, and enforce the liquidation right after the completion of the projects; and
b. send demand letters to IAs and NGOs/POs with unliquidated fund transfers.
Observation no. 8 | Advances to PS-DBM and PITC
| Delayed/non-delivery of items procured from the Procurement Service-DBM (PS-DBM) and the Philippine International Trading Corporation (PITC) resulted in the accumulated balance of fund transfers amounting to ₱1.309 billion and ₱121.917 million, respectively. | We reiterated our recommendation and Management agreed to:
a. make representation with the PS-DBM and PITC to request for the immediate delivery of the undelivered supplies, equipment and services covered by the advances made by the DENR or require them to return the cost of all undelivered supplies, if said supplies and materials are no longer be needed by the Agency due to the lapse of time; and
b. stop the practice of procuring infrastructure and land improvement projects with the PITC instead enter into an agency-to-agency agreement with the DPWH or to implement the projects, either by administration or by contract, in accordance with the provisions in RA No. 9184.
Observation no. 9 | Dormant receivable not requested for write-off
| Dormant receivable accounts, unliquidated cash advances, and fund transfers amounting to ₱30.949 million were not requested for write-off, as allowed under Section 8.2 of COA Circular No. 2016-005 dated December 19, 2016, thus, casting doubt to their validity and existence. | We recommended and the Management agreed to direct the Director of the Financial and Management Services, Bureau and Regional Directors to require their respectie Department and Regional Chief Accountants, Bureaus and PENROs Accountants to:
a. analyze the account balances regularly;
b. send demand letters when account becomes due for liquidation; and
c. consequently request for authority to write-off dormant cash advances, fund transfers and receivable accounts after complying with the documentary requirements and conditions set forth in COA Circular no. 2016-005.
Observation no. 10 | Non-insurance of physical assets with the GSIS
| The DENR-CO, four Staff Bureaus, two FAPs, eight ROs and 44 PENROs insured with the GSIS physical assets amounting to ₱3,630.528 million with corresponding insurance premiums paid in the amount of ₱46.818 million, in accordance RA No. 656, otherwise known as the "Property Insurance Law" as amended by Presidential Decree (PD) No. 245 dated July 13, 1973. However, some physical assets of three staff Bureaus, two FAPs, five ROs, and 21 PENROs in the total amount of ₱879.123 million were not insured against fire or theft with the General Insurance Fund (GIF) of the GSIS, thus, said Offices are at risk of not being indemnified in case of damage or loss of the assets. | We recommended and Management agreed to direct the Heads of the Offices concerned to provide the necessary budget for the insurance premium sufficient to cover all insurable property and cause the application for insurance thereof in faithful compliance with Sections 5 and 11 of RA No. 656.
Observation no. 11 | Non-disposal of unserviceable property
| DENR CO, ERDB, three ROs and eight PENROs have disposed their unserviceable property costing ₱7.509 million during the year while four ROs and 20 PENROs have no unserviceable property as of year-end. However, unserviceable property with a gross value of ₱47.044 million stationed in the DENR CO, three staff Bureaus, two FAPs, three ROs and 25 PENROs remained not disposed of, contrary to Section 79 of PD No. 1445, thus, exposing them to further deterioration and decreasing their realizable value. | We recommended and Management agreed to direct the Heads of the Offices concerned to take immediate action to facilitate/cause the appraisal and disposal of unserviceable property to avoid further deterioration and optimize realizable therefrom.
Observation no. 12 | Improper handling, custody and delayed disposition of confiscated products and conveyances
| The absence of a clear cut policy in the management of the Confiscated/Abandoned/Seized Goods Inventory (CASGI) on confiscated forest products, conveyances, tools and equipment resulted in the inadequate implementation of confiscated products costing ₱46.563 million in DENR CO and 16 PENROs and undetermined losses to the government due to improper handling and custody of said confiscated assets, which exposes the assets to the risk of loss due to some custodial lapses while awaiting final disposition. Moreover, confiscated equipment amounting to ₱56.800 million were left idle due to lack of dispositive plan, which resulted in wastage of resources. | We recommended and Management agreed to direct the concerned personnel of DENR CO and concerned Regional Executive Directors and PENR Officers of the 16 PENROs to:
a. issue an order directing the personnel in-charge to ensure that proper care and storage are provided for the confiscated property to preserve their economic values for the government to obtain optimum benefits therefrom;
b. in coordination with the Director for Finance, propose budget for capital outlay and/or realign budget from MOOE for the construction of safety storage of confiscated assets; and
c. conduct periodic physical count of seized property.
We further recommended and Management agreed to consider issuing supplemental guidelines and procedures over confiscation/seizure of illegaly cut forest products in such a way that it clearly defines the responsible person, its responsibility in the custody of the seized products/property and accountability over confiscated assets, and identify measures that would facilitate the speedy disposal of seized property.
Observation no. 13 | Idle/unused government property and equipment under the responsibility of the DENR Field Offices
| Property and equipment costing ₱55.595 remained idle/unused due to various reasons, thus defeats the very purpose for which such assets were purchased/constructed. | We recommended and Management agreed to direct the concerned Regional Executive Directors and PENR Officers of:
a. PENRO Aklan to:
i. identify the recipients/end-users of the six units LCD projectors, 25 units laptops, two units large format printers, five units drones, six units underwater cameras, 11 units GPSs, and four units RTK total stations procured in CYs 2019 and 2020 and issue the equipment immediately to them; and
ii. Turnover the custody of the floating pontoon together with its accessories and anchorage to the LGU of Malay either by donation or thru usufruct agreement so that the property shall be properly maintained and safeguarded;
b. PENRO Kalinga to fast track the installation of science base watershed instruments;
c. PENRO Davao del Norte to expedite the utilization of the building constructed for DENR-CENRO New Corella to ensure that government's scarce resources are fully maximized, thereby realizing the purpose for which said Agency's project was implemented; and
d. Region XII to contact the supplier as soon as possible to schedule the assessment and repair of the equipment and for them to conduct hands-on traninings on the uses, applications and operations of the equipment.
Observation no. 14 | Delayed/Non-submission of copy of government contracts
We recommended and Management agreed to direct the Heads of Offices concerned to submit copies of perfected contracts and POs with all documents forming part thereof to the audit teams concerned within five (5) days from execution/issuance prescribed in COA Circular No. 2009-01 to enable the timely review and evaluation of these contracts as well as the POs issued.
ERDB, three ROs and 15 PENROs submitted on time 3,717 government contracts and 3,359 purchase orders amounting to ₱429,469 million and ₱266.854 million, respectively. However, 2,606 government contracts and 2,720 purchase orders amounting to ₱547.261 million and ₱1,218.103 million, respectively, were not submitted by the DENR CO, three staff bureaus, four ROs and 21 PENROs within the prescribed period, with delays ranging from one to 183 days while 725 contracts were not submitted to COA for review, as required under COA Circular No. 2009-001. Hence, precluding the timely review and evaluation of the contract documents, such that any defects could not be rectified immediately.
Observation no. 15 | Proper withholding and timely remittance of GSIS contributions and loans
| The DENR CO, two staff Bureaus, 10 ROs and 54 PENROs deducted properly and remitted without delay to the Government Service Insurance System (GSIS) the personal share and loans of employees amounting to ₱488.105 million and ₱314.546 million, respectively, in accordance with RA No. 8291, the GSIS Act of 1997. Likewise, the employer's share amounting to ₱147.221 million was remitted without delay. However, there are prior years' balances that are subject for reconciliation and remittance amounting to ₱3.823 million in two Staff Bureaus, four ROs and ten PENROs. | Nonetheless, we recommended and Management agreed to instruct the Accountants of concerned DENR offices to determine the composition of the prior years' unremitted balance of the Due to GSIS account and immediately remit the same to the GSIS in compliance with RA No. 8291 and/or prepare adjusting journal entries, if necessary.
Observation no. 16 | Withholding and remittance of PhilHealth contributions and employer's share
| The DENR CO, two staff Bureaus, 11 ROs and 68 PENROs deducted properly and remitted without delay the PhilHealth personal share of employees amounting to ₱60.786 million in accordance with RA No. 7875, as amended by RA No. 7875, as amended by RA No. 9241 (National Health Insurance Act of 1995). However, there are prior years' balances, that are subject for reconciliation and remittance amounting to ₱0.408 million in two Staff Bureaus, Region VI and two PENROs. | We recommended and Management agreed to instruct the Accountant of the concerned Offices to:
a. immediately reconcile the prior years' unremitted amount of the premium contribution of its employees with the Philippine Health Insurance Corporation, in compliance with RA No. 7875 as amended by RA No. 9241, and remit the same, if necessary; and
b. regularly monitor and keep track of the withheld and remitted amounts to Philhealth.
Observation no. 17 | Proper withholding and timely remittance of Pag-IBIG contributions and loans
| The DENR CO, two staff Bureaus, 11 ROs and 64 PENROs observed proper deductions and timely remittances of the Pag-IBIG personal share and loans of employees amounting to ₱100.325 million and ₱108.565 million, respectively, in accordance with RA No. 7875, as amended by RA No. 9679. However, there are prior years' balances, that are subject for reconciliation and remittance amounting to ₱1.439 million in the two staff Bureaus, three ROs and three PENROs. | We recommended and Management agreed to instruct the Accountant to determine the composition of the unremitted balance pertaining to prior years of the Due to Pag-IBIG account and immediately remit the same to the Pag-IBIG in compliance with RA No. 9679 and make the necessary adjusting entries, if necessary.
Observation no. 18 | Proper withholding and timely remittance of taxes
| The DENR CO, two staff Bureaus, 12 ROs and 55 PENROs properly withheld and remitted without delay the taxes on gross compensation income from officials and employees and government purchases and contract of services from suppliers/contractors amounting to ₱364.959 million and ₱218.186 million, respectively, in accordance with Revenue Regulation No. 10-2008 dated July 8, 2008. However, there are unreconciled balances, unequal withholding and remittances and delay or non-remittance of withholding taxes amounting to ₱11.247 million in two staff Bureaus, three ROs and three PENROs. | We recommended and Management agreed to instruct the Accountant of:
a. the concerned offices to determine the composition of the unremitted balance pertaining to prior years of the Due to BIR account and immediately remit the same to the BIR in compliance with tax laws and regulations and make the necessary adjusting entries, if necessary; and
b. DENR-NCR to review and reconcile the prior year's tax deficiency.
Observation no. 20 | Non-allocation and/or utiliation fo fund for GAD programs/activities
| The DENR CO, LMB, four ROs and eight PENROs did not allocate five percent of the total appropriations of their agency budget for GAD programs and activities contrary to Section 31 of the GAA for FY 2020. Moreover, DENR CO, BMB, Region I and three PENROs has GAD Plan and Budget and Accomplishments Report but not endorsed by PCW, and the attribution of the NGP in the GAD Plan and Budget of the Region XIII and PENRO Davao del Norte has no well-defined gender issue thus, the evaluation of the GAD programs/ projects/related activities and cost incurred could not be made. | We recommended and Management agreed to direct the GAD Focal Point System at the DENR CO, Bureaus, ROs and PENROs to:
a. allocate at least five percent of the agency budget for the formulation and implementation of GAD Plan;
b. ensure that the Annual GPB shall be submitted to the PCW for review to have a PCW-endorsed GPB in the future;
c. assess the gender-responsiveness of the eNGP projects using the PIMME (HGDG Boxes 16 and 17); and
d. provide data on actual accomplishments and amount expended for all of the GAD activities and that the AR shall be fully supported with the financial details and documents.
Observation no. 21 | Non-allocation and/or utilization of fund for SCPD programs/activities
| THE DENR CO, two Staff Bureaus, 12 ROs and 51 PENROs spent ₱7.809 million in the implementation of the activities for the senior citizens and Persons with Disability (SCPD). However, RO IV-B and six PENROs did not allocate budget nor formulate any plans, projects and programs intended for the benefit of SCPD for CY 2020. | We recommended and Management agreed to instruct the:
a. Regional Director concerned to allocate budget and formulate plans, projects and programs; and
b. Region IV-B to cause the full implementation of the activities indicated therein for the benefit of the SCPD sector within the Agency as well as those who form part of its clientele.
Observation no. 22 | Receipt and utilization of Disaster Related Fund
| The DENR have not received funds for the Disaster Risk Reduction and Management in CY 2020 except for DENR RO X that received an amount of ₱0.542 million for the Task Force Bangon Marawi. However, said fund was used to procure various computer supplies instead of spending for expenses related to disaster risk reduction or mitigation, and prevention and preparedness activities in accordance to Section 22 of RA 10121. | We recommended and Management agreed to direct the Regional Executive Director of DENR RO X to:
a. refrain form charging unrelated expenses to the TFBM Fund and see to it that all disbursements from the trust fund are in accordance with the intended purpose; and
b. ensure that all future procurement chargeable to DRRM funds are in accordance with the items remunerated in Section 22 of RA 10121.
Observation no. 25 | Audit Suspension, disallowances, charges and settlement
| Suspension, disallowances and charges in audit of various transactions amounting to ₱158.915 million, ₱229.882 million and ₱72.550 million, respectively, remained unsettled at year-end. | We reiterated our previous years' recommendation and Management agreed to:
• ensure compliance with laws, rules and regulations to avoid audit suspensions, disallowances and charges; and
• adhere to the provision of the RRSA as prescibed under COA Circular No. 2009-006 dated September 15, 2009, requiring the settlement of suspensions, disallowances and charges within the prescribed period to prevent accumulation of unsettled NSs, NDs and NCs.