## Sheet1
Department of Enviroment and Natural Resources
Office of the Secretary (DENR-OSEC)
Visayas Avenue, Quezon City
AGENCY ACTION PLAN and
STATUS of IMPLEMENTATION
Audit Observations and Recommendations
For the Calendar Year 2018
As of ___________________________
Ref. | Audit Observations | Audit Recommendations | Agency Action Plan |  |  |  | Status of Implementation | Reason for Partial/Delay/Non-Implementation of action, if applicable | Action Taken/Action to be Taken
|  |  | Action Plan | Person/ Dept. Responsible | Target Implementation Date
[5 empty] | From | To
Observation No. 1 | Incurrence of commitment fee - ₱10.707 million | We recommended and Management agreed to direct the Foreign-Assisted and Special Projects Services (FASPS) Office to require:
The FMP and INREMP, both foreign-assisted projects, reported cumulative physical progress of only 76.15 and 38 percent against the targets of 98.58 and 78 percent, respectively, as of December 31, 2018, which caused the government commitment fee of ₱10.707 million for CY 2018
CAAR 2018 pages 4-6 |  | i. the head of FMP:
• to conduct periodic reviews to ensure that bottlenecks and issues affecting the project implementation are immediately addressed; and
• develop catch-up plan and fast track the implementation of the various components of the project to improve the physical progress towards integrating conservation and development-oriented activities with full participation and capacitation of local communities.
ii. the heads of INREMP and FMP to constantly monitor the implementation of Project activities to avoid further incurrence of commitment fee, and ensure attainment of project objectives and timely completion of the Projects in CYs 2020 and 2022, respectively; and
iii. The FASPS Director to consider project readiness before submitting design/proposal for future projects to ensure timely implementation of project activities.
Observation No. 2 | Excessive allotments in CO and deficiencies on sub-allotments to Bureaus and ROs | We recommended and Management agreed to direct:
a. the DENR-CO to: (i) stop the practice of sub-alloting to ROs, PENROs, and Bureaus its allotment for NGP/eNGP and (ii) require the submission of approved WFP which would be the basis of the sub-allotment; and
Out of the ₱7.104 billion allotments of DENR-CO intended for the implementation of the NGP and eNGP for CYs 2011-2018, ₱5.295 billion or 74.54 percent were sub-alloted to the ROs and Bureaus. Deficiencies were noted on these sub-allotment such as: (a) non-alignment of the purpose of the sub-allotments amounting to ₱168.101 million; (b) absence of Work and Financial Plan for the sub-allotment to FMB amounting to ₱229.276 million; (c) subsequent transfer of ₱20.067 million by FMB to ROs and PENROs of the sub-allotment received from DENR-CO; and (d) purpose of fund transfer amounting to ₱7.720 million was not in accordance with the purpose of the sub-allotment from DENR-CO.
CAAR 2018 pages 8-11
b. the FMB to: (i) prepare and submit the corresponding WFP; (ii) stop the practice of transferring its sub-allotment to ROs and PENROs and (iii) abide strictly with the documentary requirements for fund transfer.
Observation No. 3 | Improper charging of Expenditures to the NGP - ₱72.274 million | We recommended and management agreed to direct all Heads of Offices to ensure that appropriations intended for the implementation of the NGP are utilized only for the intended purpose.
Funds for the NGP were used for expenses that did not contribute to the attainment of goals and objectives of the Program, such as: (a) compensation paid to Extension Officers (EOs) hired by the DENR-CO, FMB and BMB performing functions not related to NGP in the total amount of ₱17.348 million, net of tax; and (b) various expenditures in the total amount of ₱54.926 million which were either improperly charged and/or the expenditures incurred were not used for the implementation of the Program.
CAAR 2018 pages 11-16
We also recommend that Management direct:
a. the DENR-CO, FMB and BMB to stop the practice of hiring Extension Officers whose duties and responsibilities were not for the benefit of the NGP/eNGP; and
b. the DENR-CO to redeploy the motor vehicles to the ROs which are actually implementing the NGP.
Observation No. 4 | Hiring of NGP Consultant | We recommended that the Office of the DENR Secretary conduct an investigation on the manner and circumstances surrounding the procurement and questionable payment of consultancy services and other perks given to the subject consultant and file appropriate charges against the FMB officials/personnel concerned, as warranted.
The FMB paid ₱11.447 million in engaging the services of a Filipino-Canadian consultant from July 2013 to June 2017 which is grossly disadvantageous to the agency due to: (a) inappropriate mode of procurement in hiring the services of the consultang; (b) exorbitant monthly consultancy fee paid to the consultant ranging from ₱100,000.00 to ₱385,000.00 for CYs 2013 to 2017; (c) payment of consultancy fee on a monthly basis despite non-submission of certain deliverable within the contract period; (d) lack of provisions in the consultancy contracts protecting the interest of the agency; and (e) lapses in implementing the terms of contracts, thereby casting doubt on the economical use of NGP funds in the payment of consultancy services towards effective implementation of the program.
CAAR 2018 pages 17-22
We further recommend that, henceforth, the FMB management should:
a. strictly adhere to the provisions of RA no. 9184 and Manual of Procedures for the Procurement of Consulting Services to obtain the most advantageous price for the agency; and
b. be more circumspect in the use of NGP funds and ensure that the same is used for its intended purpose.
Observation No. 5 | Weak Internal Control | We recommended and Management agreed to direct the Heads of:
Controls in the assignment of duties, agency operations and adherence to rules and regulations were lacking/not observed in some offices of the DENR.
a. the Management Division of the DENR-CO and Personnel and Property & Supply Management Division to coordinate and formulate guidelines that will strengthen the agency's policies and control procedures to safeguard public funds and ensure compliance to existing laws, rules and regulations.
CAAR 2018 pages 25-26
b. FMB and PENRO Dinagat Island to maintain and implement a sound system of intenal control through segregation of incompatible duties among their personnel; and
c. PENRO Tarlac to stop the practice of internal borrowing of ORs.
Observation No. 6 | Uncollected Revenue | We recommended and Management agreed to direct:
| Lapses in monitoring and collectionof rental from patrimonial/foreshore properties/cottages and contributions resulted in the accumulation of uncollected revenue and unremitted contributions estimated at ₱12.979 million which could have been used to finance other programs/projects of the agency. | a. the LMB Management to: (i) enforce the collection of occupational/rental fees including interest due for the delayed payments in accordance with the individual contracts; and (ii) develop a system generated computation of the receivables to facilitate collection of lease and the corresponding interests on delayed payments, to be made accessible to concerned personnel/office.
CAAR 2018 pages 26-31
b. the BMB management to require the two occupants to pay the corresponding cost of rental at the rate advantageous to the Bureau or ₱10,000.00 per month effective October 1, 2016.
c. the PENR Officer of Batangas to enjoin the CENR Officers to intensify the collection of rental fees including interest for the Foreshore Lease holders; and follow-up from the DENR Regional Office the approval of the submitted re-appraisal proposal in order to have a basis for the collection of the revised rental rates.
d. the PENRO-Camarines Sur, thru the RO No. V Legal Officer, to (i) send demand letter/s to BHC for the immediate remittance of its monthly contributions to PENRO Camarines Sur and/or initiate legal/other action to compel compliance thereof, and (ii) through the PAMB of MINP initiate review and renegotiation of the MOA as stipulated in Item III (C) thereof, taking into consideration the applicable provisions of the expanded NIPAS Act of 2018 (RA No. 11038), a system of procedures or mechanism that would enable PAMB to independently verify/validate the electric power production outputs of BHC, and other relevant factors affecting the MOA; and
e. the PENRO Catanduanes Management to:
• implement collection strategies to optimize collections from foreshore lease and occupation fees such as sending bills and demand letters and sanctions for nonpayment of rental;
• implement collection of rental fees using DENR DAO 2004-24 dated August 24, 2004 as basis of computation and DENR Memorandum dated Feb. 04, 2016;
• implement enforcement strategies and monitoring processes to ensure implementation of existing laws and guidelines such as provision of sanction for non-payment of rental fees; and
• conduct regular appraisal/re-appraisal of the foreshore area and the improvement thereon pursuant to DENR DAO 2004-24.
Observation No. 7 | Dormant, unauthorized and unnecessary bank accounts | We recommended and Management agreed to require the concerned offices to deposit the dormant/inactive cash balances, unnecessary and unauthorized trust funds to the Bureau of the Treasury after reconciling the bank and book balances.
The CO, three ROs and three PENROs did not revert nine dormant, unauthorized cash in bank accounts, unnecessary special and trust funds amounting to ₱27.649 million as of year-end, contrary to Pemanent Committee Joint Circular No. 4-2012, dated September 11, 2012, implementing EO No. 431, dated May 30, 2005 and COA Circular No. 2015-001 dated January 29, 2015.
CAAR 2018 pages 31-32
Observation No. 8 | Unliquidated cash advances | We recommended and Management agreed to direct the Heads of Offices concerned to require:
Cash advances for payroll, operating expenses, official local and foreign travels and special purpose/time-bound undertakings amounting to ₱14.966 million or 20.82 percent of the cash advances granted during the year amounting to ₱71.870 million were not liquidated in accordance with COA Circular No. 97-002 dated February 10, 1997. Also, there were unliquidated cash advances in prior years amounting to ₱2.106 million or 36.19 percent of prior year's balance of ₱5.819 million, of which ₱0.610 million were ten years and over but not requested for write-off.
a. Accountable Officers to settle their cash advances within the prescribed period; and
CAAR 2018 pages 33-34
b. Accounting Units to (i) refrain from processing additional cash advance of accountable officers with outstanding cash advance/s; (ii) validate the propriety of the long outstanding balances and request for write-off for those balances existing for over ten years and above.
Observation No. 9 | Unliquidated fund transfers to implementing agencies | We recommended and management agreed to direct the Heads of the Offices to require their Accountants to: (i) demand immediate liquidation of fund transfers from the concerned implementing agencies and return unutilized balances for projects that have been concluded, if any; and (ii) validate the existence of receivables aged 10 years or more and request for write-off of dormant accounts in accordance with the procedures under COA Circular No. 2016-005.
Fund transfers to IAs and NGOs/POs during the year for the implementation of agency's projects amounting to ₱78.912 million or 95.19 percent of the funds transferred were not liquidated. Also, there were still unliquidated fund transfers in prior years amounting to ₱598.435 million or 62.75 percent of prior year's balance of ₱953.755 million.
CAAR 2018 pages 34-36
Observation No. 10 | Non-insurance of physical assets with GSIS | We recommended that Management direct the Heads of the Offices concerned to provide the necessary budget for the insurance premium sufficient to cover all insurable properties and cause the application for insurance thereof in faithful compliance with Sections 5 and 11 of Republic Act No. 656.
The DENR-CO, three Staff Bureaus, four ROs and 19 PENROs insured with the GSIS physical assets amounting to ₱1.969 billion with corresponding insurance premiums paid in the amount of ₱11.726 million, in accordance Republic Act (RA) No. 656, otherwise known as the "Property Insurance Law" as amended by Presidential Decree No. 245 dated July 13, 1973. However, the physical assets in one RO, 22 PENROs and two foreign-assisted projects in the total amount of ₱569.724 million were not insured against fire or theft with the General Insurance Fund (GIF) of the GSIS, thus, said Offices are at risk of not being indemnified in case of damage or loss of the assets.
CAAR 2018 pages 36-38
We also recommend that Management direct the Regional Executive Director of Region IV-B and the OIC-PENR Officers of PENRO Occidental Mindoro and Palawan to instruct their respective Accountant and Property Officers to reconcile their PPE records to arrive at the correct value of insurable properties.
Observation No. 11 | Non-disposal of unserviceable property | We recommend that Management direct the Heads of the Offices concerned to take immediate action to facilitate the appraisal and disposal of unserviceable property to avoid further deterioration and realize possible income therefrom.
The LMB, four ROs and six PENROs have no unserviceable property as of year-end. However, unserviceable property with a gross value of ₱75.542 million in the CO, three ROs, and 16 PENROs remained not disposed of, contrary to Section 79 of Presidential Decree (P.D.) No. 1445, thus, exposing them to further deterioration and decreasing their realizable value.
CAAR 2018 pages 38-39
Observation No. 12 | Delayed/Non-submission of accounting and property reports | We recommended and Management agreed to direct the Heads of the Offices concerned to require their Accountants to submit the financial reports and documents within the time frame established under existing regulations for audit purposes.
Accounting and Property reports with their supporting documents were submitted on time in three ROs and 11 PENROs. However, the same reports were not submitted or submitted late by one to 747 days in the CO, LMB, five ROs and 25 PENROs.
CAAR 2018 pages 40-41
Observation No. 13 | Delayed/Non-submission of copy of government contracts | We recommended and Management agreed to direct the Heads of Offices concerned to submit copies of perfected contracts and POs with all documents forming part hereof to the audit teams within the prescribed period to enable the timely review and evaluation of these documents.
Copy of government contracts and their supporting documents totaling 4,553 with corresponding amount of ₱719.866 million were not submitted within the prescribed period, with delays ranging from one to 362 days. Likewise, there was a delay ranging from one to 393 days in the submission of Purchase Orders totalling 2,131 with corresponding amount of ₱99.860 million.
CAAR 2018 pages 41-43
Observation No. 14 | Non-allocation and/or utilization of fund GAD programs/activities | We recommended and Management agreed to direct the GAD Focal Point System (GFPS) and/or DENR officials concerned to: (i) allocate at least five percent of the agency budget for the formulation and implementation of GAD Plan and (ii) maximize utilization of GAD allocated budget to be more responsive in addressing gender issues.
The CO, FMB, four ROs and 15 PENROs did not allocate five percent of the total appropriations of their agency budget for GAD programs and activities, contrary to Section 30 of the General Appropriations Act (GAA) for FY 2018. Similaryly, the FASPS management failed to allocate 5-30 percent of the total appropriations of ₱995,772,000 overseas development assistance for the implementation of INREMP programs and activities. Moreover, not all planned activities were implemented due to low utilization of the allocated fund in DENR-CO, three Staff Bureaus, four Regional Offices and nine PENROs.
CAAR 2018 pages 43-44
Observation No. 15 | Allocation and/or utilization of fund for SCPD programs/activities | We recommended and Management agreed to continue giving importance to the implementation of the program/project/activities intended for SCPD, particularly the provision of facilities which will reasonably enhance the mobility, safety and welfare of the senior citizens and the differently-abled persons.
The CO, four Staff Bureaus, 11 ROs and 30 PENROs spent ₱7.349 million in the implementation of the activities for the Senior Citizens and Persons with Disability (SCPD). However, 16 PENROs did not allocate budget nor formulate any plans, projects and programs intended for the benefit of SCPD for CY 2018.
CAAR 2018 pages 44
Observation No. 16 | Appropriateness of mode of procurement used | We recommended and Management agreed to require the concerned Offices to observe strict compliance with the provisions of R.A. No. 9184 and its IRR in the procurement of goods, consultancy services and infrastructure projects.
The CO, ERDB, RO III and six PENROs complied with the requirement on the appropriateness of mode of procurement of goods, consultancy services and infrastructure projects with a total amount of ₱477.840 million. However, the mode of procurement of goods, consultancy services and infrastructure projects with a total amount of ₱59.007 million in four ROs and eight PENROs were not in accordance with RA No. 9184 and its IRR in the procurement of goods, consultancy services and infrastructure projects.
CAAR 2018 pages 45
Observation No. 17 | Posting of Programs/Projects/Activities | We recommended and Management agreed to direct the Heads of the Offices concerned to post detailed information on signboards, blackboards, white boards, tarpaulins, streamers, electronic boards, or similar materials in conspicuous place within the agency premises, and in the venue where the PPA is located or carried out in compliance with the provisions of COA Circular No. 2013-004.
The CO, two Staff Bureaus, two ROs and 14 PENROs notified the public of their Programs/Projects/Activities (P/P/A) amounting to ₱668.180 million through the posting of relevant information within the agencies premises, in compliance with COA Circular No. 2013-004 dated January 30, 2013. However, two ROs and four PENROs did not comply with the requirement on the posting of P/P/As.
CAAR 2018 pages 45-46
Observation No. 18 | Disbursements with incomplete documentary requirements | We recommended and Management agreed to ensure that all payments of claims are properly supported with complete/adequate documentation.
The DENR paid ₱46.882 million for transactions with incomplete/inadequate documentation or non-compliant with existing rules and regulations, thus, casting doubt on their propriety, regularity and validity.
CAAR 2018 pages 47-48
We also recommended and Management agreed to discontinue granting benefits and allowances without legal basis and those that violate existing laws, rules and regulations.
Observation No. 19 | Erroneous charging of expenses to Fund 101 Trust | We recommended and Management agreed to direct the PENRO Iloilo to:
Expenses and cash advances for the implementation of the FMP under Fund 102 GOP Counterpart and snacks during the BAC meetings of PENRO Iloilo amounting to ₱394,384.62 and ₱9,783.25, respectively, were charged against the Trust Account of Fund 101, thus, may be considered as illegal and irregular expenditures.
a. monitor and ensure that cash advances and expenses for the implementation of the FMP under Fund 102 GOP counterpart are charged only from said Fund upon receipt of the NCA/NTA;
CAAR 2018 pages 48-49
b. stop the practice of charging to Fund 101 Trust expenses not related to the purpose for which the trust was created; and
c. require the payees to refund the remaining claims for reimbursement of snacks during the BAC meetings amounting to ₱8,343.25 covered by ND and discontinue claiming expenses of similar nature.
Observation No. 20 | Audit suspensions, disallowances, charges and settlement | We reiterated our prior years' recommendation and Management agreed to:
| Suspensions, disallowances and charges in audit of various transactions amounting to ₱112.254 million and ₱61.753 million, respectively, remained unsettled. | a. comply with existing laws, rules and regulations to avoid NSs, NDs and NCs;
CAAR 2018 pages 49-51
b. adhere to the provisions of the Rules and Regulations on Settlement of Accounts (RRSA) under COA Circular No. 2009-006 dated September 15, 2009, requiring the settlement of suspensions, disallowances and charges within the prescribed period to prevent accumulation of unsettled NSs, NDs and NCs; and
c. intensify the settlement of disallowances and charges by seeking the approval of COA to pay in installment the liability under the NDs/NCs issued pursuant to COA Resolution No. 2015-031 dated August 20, 2015.
Observation No. 21 | Unadjusted/accounting errors/omissions and deficiencies | We recommended and Management agreed to require the Accountants concerned to effect the necessary adjustments on the errors/omissions with corresponding reporting documents and correct the deficiencies.
A qualified opinion was rendered on the Financial Statements due to various accounting errors/omissions and deficiencies amounting to ₱1.544 billion which exceeded the materiality level of ₱955.062 million.
CAAR 2018 pages 51-54
| Prepared by: |  | Noted by: