## Slide 1
(December 14, 2021)
Update on the Status of NHA’s Yolanda Permanent Housing Program (YPHP)
in Palawan Province

## Slide 2
Map of the Philippines

## Slide 3: Update on the Status of the Remaining House & Lot Units within the Province of Palawan under the Yolanda Permanent Housing Program (YPHP) (As of 14 December 2021)
No. | Location/Municipalities in the Province of Palawan | No. of Units for Completion | Remarks/Status |  | 
 |  |  | AO October 25, 2021 | AO December 14, 2021 | 
1. | Coron Heights Bgy. San Nicolas, Coron, Palawan | 1,470 | On-going Land Development and construction of 224 Housing Units. | On-going Land Development and construction of 500 Housing Units. 27.22% accomplished. | Processing of Environmental Permits and Clearances is on-going. (SEP/PCSD, ECC). DENR, PCSD and other concerned agencies will facilitate in the land conversion from Forestland to Alienable and Disposable.
2. | Coron Residences Bgy. San Nicolas, Coron, Palawan | 1,200 | On-going Land Development and construction of 255 Housing Units. | On-going Land Development and construction of 500 Housing Units. 27.55% accomplished. | 
3. | Villa Cambian Brgy. Cambian, Agutaya | 104 | With Notice of Award. On-going compliances prior to issuance of Notice to Proceed | - Land Classification of selected site is UPF. With Notice of Award. On-going compliances prior to issuance of Notice to Proceed. DENR, PCSD and other concerned agencies will facilitate in land classification of the selected site. | 
4. | Safari Ville Brgy. Salvacion, Busuanga | 328 | With Notice of Award. On-going compliances prior to issuance of Notice to Proceed | NTP Received by the contractor on December 6, 2021 | 
5. | San Pablo Homes Brgy. Osmeña, Culion | 796 | With Notice of Award. On-going compliances prior to issuance of Notice to Proceed | NTP Received by the contractor on December 6, 2021 | 
6. | Tarabidan Ville Bgy. San Miguel, Linapacan | 684 | With Notice of Award. On-going compliances prior to issuance of Notice to Proceed | - Land Classification of selected site is UPF. - With Notice of Award. On-going compliances prior to issuance of Notice to Proceed. - DENR, PCSD and other concerned agencies will facilitate in land classification of the selected site. | 
7. | Baldat (PGP implemented) Bgy. Baldat, Culion, Palawan | 28 | - |  | 
8. | Binudac (PGP implemented) Bgy. Binudac, Culion, Palawan | 274 | - |  | 
9. | Galoc (PGP implemented) Bgy. Galoc, Culion, Palawan | 406 | - |  | 
Total |  | 5,290 |  |  | 

## Slide 4
ON GOING LAND DEVELOPMENT AND HOUSING CONSTRUCTION IN CORON HEIGHTS, BGY. SAN NICOLAS, CORON, PALAWAN

## Slide 5
ON GOING LAND DEVELOPMENT AND HOUSING CONSTRUCTION IN CORON RESIDENCES, BGY. SAN NICOLAS, CORON, PALAWAN

## Slide 6
SAFARI VILLE
Bgy. Old Busuanga, Busuanga, Palawan

## Slide 7
SAN PABLO HOMES
Bgy. Malaking Patag, Culion, Palawan

## Slide 8: End of Presentation… THANK YOU