## Slide 1
(February 15, 2022)
Update on the Status of NHA’s Yolanda Permanent Housing Program (YPHP)
in Palawan Province

## Slide 2: Update on the Status of the Remaining House & Lot Units within the Province of Palawan under the Yolanda Permanent Housing Program (YPHP) (As of 24 February 2022)
No. | Location/Municipalities in the Province of Palawan | No. of Units for Completion |  | Remarks/Status | 
 |  |  | AO December 14, 2021 |  | AO February 15, 2022
1. | Coron Heights Bgy. San Nicolas, Coron, Palawan | 1,470 | On-going Land Development and construction of 500 Housing Units. 27.22% accomplished. | Processing of Environmental Permits and Clearances is on-going. (SEP/PCSD, ECC). DENR, PCSD and other concerned agencies will facilitate in the land conversion from Forestland to Alienable and Disposable. Work Suspended November 15, 2021 | NHA GM sent communication letter to Mr. MARCIAL C. AMARO, Jr. of DENR’s Forest Management Bureau stating AO No. 44 dated October 28, 2014 and DARAO No. 02, series of 2017. Mr. AMARO’s response dated January 4, 2022 is to maintain their previous stand for NHA to “hold in abeyance” the construction of the project within BPR until such time that the authenticity and legality of titles are proven or the impending issues and concerns on the matter are resolved. NHA MIMAROPA District researched the authenticity of the title. The Palawan Provincial Register of Deeds found out that the title is active and no encumbrances, but required that the “owner’s duplicate” be presented for them to issue CERTIFICATE OF AUTHENTICITY. NHA MIMAROPA District Office is on the process of providing the original copy of “Owner’s Duplicate Certificate”
2. | Coron Residences Bgy. San Nicolas, Coron, Palawan | 1,200 | On-going Land Development and construction of 500 Housing Units. 27.55% accomplished. |  | 
3. | Villa Cambian Brgy. Cambian, Agutaya | 104 | - Land Classification of selected site is UPF. With Notice of Award. On-going compliances prior to issuance of Notice to Proceed. DENR, PCSD and other concerned agencies will facilitate in land classification of the selected site. |  | Land Classification of selected site is UPF. With Notice of Award. On-going compliances prior to issuance of Notice to Proceed. DENR, PCSD and other concerned agencies will facilitate in land classification of the selected site.
4. | Safari Ville Brgy. Salvacion, Busuanga | 328 | NTP Received by the contractor on December 6, 2021 |  | On going processing of Development Permit On going processing of ECAN Certificate at PCSD, the site already inspected by the Engineers of PCSD.
5. | San Pablo Homes Brgy. Osmeña, Culion | 796 | NTP Received by the contractor on December 6, 2021 |  | On going processing of Development Permit, project deliberation on Members of SBBB On going processing of permits, ECAN Zoning Cert. submitted to PCSD
6. | Tarabidan Ville Bgy. San Miguel, Linapacan | 684 | - Land Classification of selected site is UPF. - With Notice of Award. On-going compliances prior to issuance of Notice to Proceed. - DENR, PCSD and other concerned agencies will facilitate in land classification of the selected site. |  | - Land Classification of selected site is UPF. - With Notice of Award. On-going compliances prior to issuance of Notice to Proceed. - DENR, PCSD and other concerned agencies will facilitate in land classification of the selected site.
7. | Baldat (PGP implemented) Bgy. Baldat, Culion, Palawan | 28 | - Completed, ready for turn-over |  | PGP update
8. | Binudac (PGP implemented) Bgy. Binudac, Culion, Palawan | 274 | - On-going implementation |  | PGP update
9. | Galoc (PGP implemented) Bgy. Galoc, Culion, Palawan | 406 | - On-going implementation |  | PGP update
Total |  | 5,290 |  |  |