## 1GD
Patrol Plan for the Conservation Areas in CENRO BROOKE'S POINT
General Data
Size of Conservation Area (ha): | Based on NAMRIA Admin Boundaries - 159, 877.29 hectares
Based on CENRO Admin Boundaries - 102,424.578 hectares (GIS generated data)
Conservation targets (10 year plan) | Reduce or minimize Forest Degradation (28,553 ha*) by 15% to mitigate shortage of water supply particularly in watershed areas
Protect and conserve remaining closed forest (1, 324.12 has*) to provide better habitat for Palawan Peacock Pheasant, Palawan hornbill, Palawan Bearcat, Palawan Bearded Pig, Philippine Pangolin and Balabac mouse deer (Pilandok)
Minimize or reduce commonly observed forest threats based on January 2017 to July 2018 data on apprehensions and/or incidence of illegal activities and threats recorded via Lawin by 20% by means of intensified patrolling activities, enforce use of legal actions for violators, intensified community education and public awareness and strengthen coordination with local government units and other government agencies, law enforcement agencies, organizations, NGOs and local communities to ensure protection of the forests, the reduction of pressure and degradation of forests and to conserve the forest resources and continuously benefit from the ecosystem services provided by these resources.
Target patrol distance (km) | 150
Target barangays and municipalities to be covered within the period | Sector 1: Municipality of So. Espanola, Sector 2: Municipality of Brooke's Point, Sector 3: Municipality of Bataraza, Sector 4: Municipality of Balabac
Approximate area of conservation area in the target area to be covered within period (ha) | Quarterly Sector 1: Municipality of So. Espanola 600 hectares, Sector 2: Municipality of Brooke's Point 600 hectares , Sector 3: Municipality of Bataraza 600 hectares, Sector 4: Municipality of Balabac 600 hectares
Period covered by this plan | 3rd Quarter (June 22 to September 21, 2023)
Name of Patrol organizer | FT I Reynaldo V. Palisoc

## 2 DENR Patrollers
Names of Patrollers and Expertise
No. |  | Expertise (threats monitoring or indicator species monitoring) | Position (FR, FT, Forester) | Employment status (JO, permanent) | Qualified to conduct patrolling
1 | LAPANGAN, LEANDRO JR. F. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
2 | GABUCO, MARK ANTHONY L. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
3 | MIRAFLOR, RUDY P. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
4 | EVINA, ELMER V. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
5 | VICENTE, ABRAHAM B. | Threats/Indicator species monitoring | FT II | PERMANENT | Yes
6 | AURINO, ENRICO III L. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
7 | VELASCO, MARK RONALD S. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
8 | TAJON, JEFFERSON B. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
9 | AMAR, FERMIN P. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
10 | CORPUZ, CONRADO SR. D. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
11 | VALDESTAMON, KENNIT FRANCIS V. | Threats/Indicator species monitoring | FT II | PERMANENT | Yes
12 | BUENAFE, CHRISTOPHER C. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
13 | CACATIAN, ROSTUM Q. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
14 | GALICIA, ARIEL D. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
15 | TUPAS, LEONALD A. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
16 | IDLANA, RJ KEITH IMMANUEL I. | Threats/Indicator species monitoring | FT I | PERMANENT | Yes
17 | VICENTE, BIMBO B. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
18 | SETIAS, JEFFREY F. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
19 | GRACIANO, APRIL ANNE T. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
20 | RONAS, RODEL A. | Threats/Indicator species monitoring | FR | PERMANENT | Yes
21 | GAMUYAO, ROLAN P. | Threats/Indicator species monitoring | FPO | COS | Yes
22 | TURINA, JANGGO | Threats/Indicator species monitoring | FPO | COS | Yes
23 | ACODILI, EDRALIN | Threats/Indicator species monitoring | FPO | COS | Yes
24 | TALATA, ALSIMAN F. | Threats/Indicator species monitoring | FPO | COS | Yes

## 3 Volunteers
Names of Volunteer Patrollers
Number | Name of community volunteer patrollers who will join regular patrolling | Expertise (threats monitoring or indicator species monitoring) | Given allowance by LGU? (yes or no?)
None

## 4 Sectors
Patrol Sectors
Patrol sectors | Name of sitio, barangay, municipility covered by sector | Approximate area of coservation area in the sector (ha) | Target threats to be recorded and addressed in the patrol sector | Target indicator species
1 | Municipality of Sofronio Española | 19768.573 | Kaingin, illegal cutting of trees, charcoal making | Palawan Peacock Pheasant, Palawan hornbill, Falcated Ground-Babbler, Citrine Canary-Flycatcher, Palawan Bearded Pig, Pangolin, Water monitor Lizard.
2 | Municipality of Brooke's Point | 35204.904 | Kaingin, illegal cutting of trees, charcoal making | Palawan Bearded Pig, Pangolin, Water monitor Lizard , Palawan hornbill, Falcated Ground-Babbler, Citrine Canary-Flycatcher
3 | Municipality of Bataraza | 23522.976 | Kaingin, illegal cutting of trees, charcoal making, tanbarking | Palawan Bearded Pig, Water monitor Lizard, Falcated Ground-Babbler, Citrine Canary-Flycatcher, Palawan Peacock Pheasant.
4 | Municipality of Balabac | 23928.125 | Kaingin, illegal cutting of trees, charcoal making, tanbarking | Philippine Pangolin, Balabac mouse deer (Pilandok), Water monitor Lizard, Palawan hornbill.
TOTAL |  | 102,424.578 hectares

## 5 Teams
Patrol Teams
Number | Office | Name of forest rangers, other DENR staff and volunteers who will conduct regular patrolling | Expertise (threats monitoring or indicator species monitoring) | Sector assignment | Team leader | Recorder
1 | DENR | LAPANGAN, LEANDRO JR. F. | Threats/Indicator Species Monitoring | 1 | ü
2 | DENR | GABUCO, MARK ANTHONY L. | Threats/Indicator Species Monitoring | 1 |  | ü
3 | DENR | MIRAFLOR, RUDY P. | Threats/Indicator Species Monitoring | 1
4 | DENR | EVINA, ELMER V. | Threats/Indicator Species Monitoring | 1
5 | DENR | VICENTE, ABRAHAM B. | Threats/Indicator Species Monitoring | 2 | ü
6 | DENR | AURINO, ENRICO III L. | Threats/Indicator Species Monitoring | 2
7 | DENR | VELASCO, MARK RONALD S. | Threats/Indicator Species Monitoring | 2
8 | DENR | TAJON, JEFFERSON B. | Threats/Indicator Species Monitoring | 2 |  | ü
9 | DENR | AMAR, FERMIN P. | Threats/Indicator Species Monitoring | 2
10 | DENR | CORPUZ, CONRADO SR. D. | Threats/Indicator Species Monitoring | 2
11 | DENR | VALDESTAMON, KENNIT FRANCIS V. | Threats/Indicator Species Monitoring | 3 | ü
12 | DENR | BUENAFE, CHRISTOPHER C. | Threats/Indicator Species Monitoring | 3
13 | DENR | CACATIAN, ROSTUM Q. | Threats/Indicator Species Monitoring | 3 |  | ü
14 | DENR | GALICIA, ARIEL D. | Threats/Indicator Species Monitoring | 3
15 | DENR | TUPAS, LEONALD A. | Threats/Indicator Species Monitoring | 3
16 | DENR | IDLANA, RJ KEITH IMMANUEL I. | Threats/Indicator Species Monitoring | 4 | ü
17 | DENR | VICENTE, BIMBO B. | Threats/Indicator Species Monitoring | 4
18 | DENR | SETIAS, JEFFREY F. | Threats/Indicator Species Monitoring | 4 |  | ü
19 | DENR | GRACIANO, APRIL ANNE T. | Threats/Indicator Species Monitoring | 1-4
20 | DENR | RONAS, RODEL A. | Threats/Indicator Species Monitoring | 1-4
21 | DENR | GAMUYAO, ROLAN P. | Threats/Indicator Species Monitoring | 1
22 | DENR | TURINA, JANGGO | Threats/Indicator Species Monitoring | 2
23 | DENR | ACODILI, EDRALIN | Threats/Indicator Species Monitoring | 3
24 | DENR | TALATA, ALSIMAN F. | Threats/Indicator Species Monitoring | 4

## Map1 Patrol Sectors
Patrol Sectors
Legend
|  | Sector 1 | Sector 2 | Sector 3 | Sector 4

## Map2 Patrol Map
Patrol Map
Legend
|  | Team 1 Threats/Indicator Species focused | Team 3 Threats/Indicator Species focused
|  | Team 2 Threats/Indicator Species focused | Team 4 Threats/Indicator Species focused
June 22 to July 21; July 22 to August 21; August 22 to September 21, 2023
- Bgy. Sumbiling/ BonoBono/ Rio Tuba/ Iwahig/ Tarusan/ Malihud, Bataraza, Palawan
June 22 to July 21; July 22 to August 21; August 22 to September 21, 2023
- Bgy. Pulot Interior/ Punang/ Panitian/ Isumbo/ Abo-Abo, Sofronio Española, Palawan
June 22 to July 21; July 22 to August 21; August 22 to September 21, 2023
- Bgy. Aribungos/ Maasin/ Calasaguen/ Samariniana/ Salogon/ Malis/ Mainit/ Ipilan, Brooke's Point, Palawan
June 22 to July 21; July 22 to August 21; August 22 to September 21, 2023
- Bgy. Agutayan, Indalawan, Malaking Ilog, Salang and Catagupan, Balabac, Palawan

## 6Skdt
Schedule of Patrols, Teams and Routes Assignment for the period
Month | Week | Team | Activity/Type of patrol (threats focused or indicator species-focused, or coordination/response) | Specific routes (name sector number and specific sitio or barangay and municipality) | Target distance (km)
JULY | June 22 to July 21, 2023 | Team 1 | Threats/Indicator Species focused | Bgy. Pulot Interior/ Punang/ Panitian/ Isumbo/ Abo-Abo, Sofronio Española, Palawan | 12.5
| June 22 to July 21, 2023 | Team 2 | Threats/Indicator Species focused | Bgy. Aribungos/ Maasin/ Calasaguen/ Samariniana/ Salogon/ Malis/ Mainit/ Ipilan, Brooke's Point, Palawan | 12.5
| June 22 to July 21, 2023 | Team 3 | Threats/Indicator Species focused | Bgy. Sumbiling/ BonoBono/ Rio Tuba/ Iwahig/ Tarusan/ Malihud, Bataraza, Palawan | 12.5
| June 22 to July 21, 2023 | Team 4 | Threats/Indicator Species focused | Bgy. Agutayan, Indalawan, Malaking Ilog, Salang and Catagupan, Balabac, Palawan | 12.5
AUGUST | July 22 to August 21, 2023 | Team 1 | Threats/Indicator Species focused | Bgy. Pulot Interior/ Punang/ Panitian/ Isumbo/ Abo-Abo, Sofronio Española, Palawan | 12.5
| July 22 to August 21, 2023 | Team 2 | Threats/Indicator Species focused | Bgy. Aribungos/ Maasin/ Calasaguen/ Samariniana/ Salogon/ Malis/ Mainit/ Ipilan, Brooke's Point, Palawan | 12.5
| July 22 to August 21, 2023 | Team 3 | Threats/Indicator Species focused | Bgy. Sumbiling/ BonoBono/ Rio Tuba/ Iwahig/ Tarusan/ Malihud, Bataraza, Palawan | 12.5
| July 22 to August 21, 2023 | Team 4 | Threats/Indicator Species focused | Bgy. Agutayan, Indalawan, Malaking Ilog, Salang and Catagupan, Balabac, Palawan | 12.5
SEPTEMBER | August 22 to September 21, 2023 | Team 1 | Threats/Indicator Species focused | Bgy. Pulot Interior/ Punang/ Panitian/ Isumbo/ Abo-Abo, Sofronio Española, Palawan | 12.5
| August 22 to September 21, 2023 | Team 2 | Threats/Indicator Species focused | Bgy. Aribungos/ Maasin/ Calasaguen/ Samariniana/ Salogon/ Malis/ Mainit/ Ipilan, Brooke's Point, Palawan | 12.5
| August 22 to September 21, 2023 | Team 3 | Threats/Indicator Species focused | Bgy. Sumbiling/ BonoBono/ Rio Tuba/ Iwahig/ Tarusan/ Malihud, Bataraza, Palawan | 12.5
| August 22 to September 21, 2023 | Team 4 | Threats/Indicator Species focused | Bgy. Agutayan, Indalawan, Malaking Ilog, Salang and Catagupan, Balabac, Palawan | 12.5
|  |  |  | Total: | 150