## 1GD
Patrol Plan for the Natural Forest in CENRO Roxas, Palawan
General Data
Size of natural forest area (ha): | 135,681 ha
Conservation targets | 1. Reduce forest degradation by 25 % within the next 10 years
1. Reduce forest loss/ deforestation by 25 % within the next 10 years
3. Zero or no expansion of existing kaingin farm starting 2016
Target patrol distance (km) | 162.8 per quarter
Target Barangays and Municipalities to be covered within the period | Brgy. Abaroan, Antonino, Magara, Nicanor Zabala, Dumarao, and Tinitian in Roxas; Brgy. Port Barton, Caruray, Alimanguan, San Isidro in San Vicente; Brgy. Tanatanaon, Capayas and Sta. Maria in Dumaran
Approximate area of natural forest in the target area to be covered within period (ha) | 6,784 ha
Period covered by this plan | 3RD Quarter C.Y. 2023
Name of Patrol organizer | Diogenes A. Esquillo, Chief, Monitoring Enforcement Section
Notes
Each CENRO will have one Patrol Plan per quarter
Fill in target patrol distance, target baranggays and approximate area to be covered within the planning period
once patrol routes and schedule have been completed

## 2DENR
Names of patrollers and expertise
Number |  | Expertise (threats monitoring or indicator species monitoring) | Position (FR, FT, Forester) | Employment status (JO, permanent) | Qualified to conduct patrolling | Present in this workshop (yes or no?)
1 | JARDIN, ENRIQUE G. | Threats monitoring/Indicator species monitoring | FR | PERMANENT | Yes | Yes
2 | PADRONES, CHRISTOPHER T. | Threats monitoring | FR | PERMANENT | Yes | Yes
3 | TAJON, JAMES S. | Threats monitoring | FR | PERMANENT | Yes | Yes
4 | GABAYAN, ARMANDO R. | Threats monitoring | FR | PERMANENT | Yes | Yes
5 | ORTEGA, MARK ANTHONY G. | Threats monitoring | FR | PERMANENT | Yes | Yes
6 | MERCADER, ROY T. | Threats monitoring | FT II | PERMANENT | Yes | Yes
7 | BACALLA, LEMUEL L. | Threats monitoring | FR | PERMANENT | Yes | No
8 | YAQUITIN, ROGELIO B. | Threats monitoring | TREE MARKER | PERMANENT | Yes | Yes
9 | MARQUEZ, MARCO ANGELO M. | Threats monitoring | FR | PERMANENT | Yes | Yes
10 | RABANG, CHARLIE A. | Threats monitoring | FR | PERMANENT | Yes | Yes
11 | MADURO, ALVIN U. | Threats monitoring | FR | PERMANENT | Yes | No
12 | SOTOZA, MARKWILLIAMS R. | Threats monitoring | FR | PERMANENT | Yes | No
13 | TABANGAY, ALONSO A. | Threats monitoring | FR | PERMANENT | Yes | No
14 | LLANIGUEZ, ROMMEL ALLAN | Threats monitoring | FR | PERMANENT | Yes | No
15 | GIGANTO, RYAN P. | Threats monitoring | FR | PERMANENT | Yes | No
16 | MABITASAN, RONNIE JAN IAN B. | Threats monitoring | FR | PERMANENT | Yes | No
17 | SADDIN, MERMA J. | Threats monitoring | FR | PERMANENT | Yes | No
18 | MANLIGUEZ, JETER E. | Threats monitoring | FR | PERMANENT | Yes | No
19 | AQUINO, JOVEN B. | Threats monitoring | FPO | JO | Yes | No
20 | MICHAEL VALDEZ | Threats monitoring | FPO | JO | Yes | No
21 | SEÑO, JERICK RON | Threats monitoring | FPO | JO | Yes | No
22 | FALLARCUNA, JESS MARK | Threats monitoring | FPO | JO | Yes | No
add more rows as needed
Notes
Include names of all forest rangers but indicate those present in the workshop in column D

## 3Vols
Names of volunteer patrollers
Number | Name of community volunteer patrollers who will join regular patrolling | Expertise (threats monitoring or indicator species monitoring) | Given allowance by LGU? (yes or no?)
1
2
3
4
5
6
7
8
9
[add more rows as needed]
Note
Do this later if you do not know the names of volunteer forest guards

## 4Sctors
Patrol sectors
Patrol sectors | Name of sitio, barangay, municipility covered by sector | Approximate area of natural forest in the sector (ha) | Target threats to be recorded and addressed in the patrol sector | Target indicator species
1 | POBLACION - BARANGAY TINITIAN, ROXAS, PALAWAN | 26060 | Kaingin, illegal cutting of trees, charcoal making, girdling of mangroves, conversion of mangrove area to fish ponds | PHILIPPINE PANGULING; SQUIRREL; PALAWAN PEACOCK PEASANT; JUGNLE FOWL; WILD BOAR; TABON BIRD; PHILIPPINE MACAQUE
2 | POBLACION - BARANGAY BAGONG BAYAN, ROXAS, PALAWAN | 26060 | Kaingin, illegal cutting of trees, charcoal making, girdling of mangroves, conversion of mangrove area to fish ponds | KATALA; FRESH WATER TURTLE; PHILIPPINE PANGULING; SQUIRREL; PALAWAN PEACOCK PEASANT; JUGNLE FOWL; WILD BOAR; TABON BIRD; PHILIPPINE MACAQUE
3 | SAN VICENTE, PALAWAN | 39090 | Kaingin, illegal cutting of trees, charcoal making, girdling of mangroves, conversion of mangrove area to fish ponds | PHILIPPINE PANGULING; SQUIRREL; PALAWAN PEACOCK PEASANT; JUGNLE FOWL; WILD BOAR; TABON BIRD; PHILIPPINE MACAQUE
4 | ARACELI AND DUMARAN, PALAWAN | 39090 | Kaingin, illegal cutting of trees, charcoal making, girdling of mangroves, conversion of mangrove area to fish ponds | KATALA; PHILIPPINE PANGULING; SQUIRREL; PALAWAN PEACOCK PEASANT; JUNGLE FOWL; WILD BOAR; TABON BIRD; PHILIPPINE MACAQUE
[add rows if needed]
Things to consider when identifying sectors:
Conservation objectives and targets in the Forest Conservation Area Plan
Locations of forest loss, forest degradation and forest enhancement (see map 1)
Number of teams that can be formed

## map1
Patrol sectors
Insert indicative squares/rectangels in the targeted patrol sectors
Notes
Indicate in the map the planned routes
Legend
Sector 1
Sector 2
Sector 3
Sector 4
Sector 1
Poblacion-Brgy. Tinitian
26,060 ha
Sector 2
Poblacion-Brgy. Bagong Bayan
26,060 ha
Sector 3
San Vicente
39,090 ha
Sector 4
Araceli-Dumaran
39,090 ha

## 5Tms
Patrol teams
Number | Office | Name of forest rangers, other DENR staff and volunteers who will conduct regular patrolling | Expertise (threats monitoring or indicator species monitoring) | Qualified? | Present in workshop | Sector assignment | Team leader | Recorder
1 | DENR | JARDIN, ENRIQUE G. | Threats monitoring/Indicator species monitoring | Yes | Yes | 2
2 | DENR | PADRONES, CHRISTOPHER T. | Threats monitoring | Yes | Yes | 4
3 | DENR | TAJON, JAMES S. | Threats monitoring | Yes | No | 3 | Yes
4 | DENR | GABAYAN, ARMANDO R. | Threats monitoring/Indicator species monitoring | Yes | Yes | 4
5 | DENR | ORTEGA, MARK ANTHONY G. | Threats monitoring | Yes | Yes | 2
6 | DENR | MERCADER, ROY T. | Threats monitoring | Yes | Yes | 2 | Yes
7 | DENR | BACALLA, LEMUEL L. | Threats monitoring | Yes | Yes | 4 | Yes
8 | DENR | YAQUITIN, ROGELIO B. | Threats monitoring | Yes | Yes | 3
9 | DENR | MARQUEZ, MARCO ANGELO M. | Threats monitoring | Yes | Yes | 4 |  | Yes
10 | DENR | RABANG, CHARLIE A. | Threats monitoring | Yes | No | 2 |  | Yes
11 | DENR | MADURO, ALVIN U. | Threats monitoring | Yes | No | 3 |  | Yes
12 | DENR | SOTOZA, MARKWILLIAMS R. | Threats monitoring | Yes | No | 1 |  | Yes
13 | DENR | TABANGAY, ALONSO A. | Threats monitoring | Yes | No | 1 | Yes
14 | DENR | LLANIGUEZ, ROMMEL ALLAN | Threats monitoring | Yes | No | 1
15 | DENR | GIGANTO, RYAN P. | Threats monitoring | Yes | No | 3
16 | DENR | MABITASAN, RONNIE JAN IAN B. | Threats monitoring | Yes | No | 1
17 | DENR | SADDIN, MERMA J. | Threats monitoring | Yes | No | 2
18 | DENR | MANLIGUEZ, JETER E. | Threats monitoring | Yes | No | 4
19 | DENR | AQUINO, JOVEN B. | Threats monitoring | Yes | No | 1
20 | DENR | VALDEZ, MICHAEL | Threats monitoring | Yes | No | 2
21 | DENR | SEÑO, JERICK RON | Threats monitoring | Yes | No | 4
22 | DENR | FALLARCUNA, JESS MARK | Threats monitoring | Yes | No | 3
[add more rows as needed] | Vol
Notes
Add more rows between DENR and Vols if needed
Include names of all forest rangers but indicate those presnet in the workshop in column D
Put an x after the name of the team leader and recorder once the teams have been formed

## 6Skdt
Schedule of patrols, teams and routes assignment for the period
Month | Week | Team (indicate number) | Activity/Type of patrol (threats focused or indicator species-focused, or coordination/response) | Specific routes (name sector number and specific sitio or barangay and municipality) | Target distance (km)
JULY | Week 1 | Team 1 | Threats focused | Sector 1: So. Matalangao, Brgy. Abaraoan, Roxas | 3
JULY | Week 1 | Team 2 | Threats focused | Sector 2: So. Maraibo, Brgy. Antonino, Roxas | 3
JULY | Week 1 | Team 3 | Threats focused | Sector 3: So. Pamuayan, Brgy. Port Barton, San Vicente | 3
JULY | Week 1 | Team 4 | Threats focused | Sector 4: So. Manggahan, Brgy. Tanataon, Dumaran | 3
JULY | Week 2 | Team 1 | Threats focused | Sector 1: So. Little Caramay, Brgy. Magara, Roxas | 3
JULY | Week 2 | Team 2 | Threats focused | Sector 2: So. Maragoc, Brgy. Antonino, Roxas | 3
JULY | Week 2 | Team 3 | Threats focused | Sector 3: So. Kawakayan, Brgy. New Canipo, San Vicente | 3
JULY | Week 2 | Team 4 | Threats focused | Sector 4: So. Lumiliba, Brgy. Capayas, Dumaran | 3
JULY | Week 3 | Team 1 | Threats focused | Sector 1: So. Upper Marirong, Brgy. Nicanor Zabala, Roxas | 3
JULY | Week 3 | Team 2 | Threats focused | Sector 2: So. Stockpile, Brgy. Dumarao, Roxas | 3
JULY | Week 3 | Team 3 | Threats focused | Sector 3: So. JMP, Brgy. Alimanguan, San Vicente | 3
JULY | Week 3 | Team 4 | Threats focused | Sector 4: So. Centro, Brgy. Magsaysay, Dumaran | 3
JULY | Week 4 | Team 1 | Threats focused | Sector 1: So. Bayugon, Brgy. Tinitian, Roxas | 3
JULY | Week 4 | Team 2 | Threats focused | Sector 2: So. Durian, Brgy. Mendoza, Roxas | 3
JULY | Week 4 | Team 3 | Threats focused | Sector 3: So. Tagpis and Bokbok, Brgy. San Isidro, San Vicente | 3
JULY | Week 4 | Team 4 | Threats focused | Sector 4: So. Malaking Patag, Brgy. Sta. Maria, Dumaran | 3
AUGUST | Week 1 | Team 1 | Threats focused | Sector 1: So. Matalangao, Brgy. Abaraoan, Roxas | 3
AUGUST | Week 1 | Team 2 | Threats focused | Sector 2: So.Maraibo, Brgy. Antonino, Roxas | 3
AUGUST | Week 1 | Team 3 | Threats focused | Sector 3: So. Pamuayan, Brgy. Port Barton, San Vicente | 3
AUGUST | Week 1 | Team 4 | Threats focused | Sector 4: So. Manggahan, Brgy. Tanataon, Dumaran | 3
AUGUST | Week 2 | Team 1 | Threats focused | Sector 1: So. Little Caramay, Brgy. Magara, Roxas | 3
AUGUST | Week 2 | Team 2 | Threats focused | Sector 2: So. Maragok, Brgy. Antonino, Roxas | 3
AUGUST | Week 2 | Team 3 | Threats focused | Sector 3: So. Decala, Brgy. Caruray, San Vicente | 3
AUGUST | Week 2 | Team 4 | Threats focused | Sector 4: So. Lumiliba, Brgy. Capayas, Dumaran | 3
AUGUST | Week 3 | Team 1 | Threats focused | Sector 1: So. Upper Marirong, Brgy. Nicanor Zabala, Roxas | 3
AUGUST | Week 3 | Team 2 | Threats focused | Sector 2: So. Stockpile, Brgy. Dumarao, Roxas | 3
AUGUST | Week 3 | Team 3 | Threats focused | Sector 3: So. JMP, Brgy. Alimanguan, San Vicente | 3
AUGUST | Week 3 | Team 4 | Threats focused | Sector 4: So. Centro, Brgy. Magsaysay, Dumaran | 3
AUGUST | Week 4 | Team 1 | Threats focused | Sector 1: So. Bayugon, Brgy. Tinitian, Roxas | 3
AUGUST | Week 4 | Team 2 | Threats focused | Sector 2: So. Subingao, Brgy. Dumarao, Roxas | 3
AUGUST | Week 4 | Team 3 | Threats focused | Sector 3: So. Tagpis and Bokbok, Brgy. San Isidro, San Vicente | 3
AUGUST | Week 4 | Team 4 | Threats focused | Sector 4: So. Malaking Patag, Brgy. Sta. Maria, Dumaran | 3
SEPTEMBER | Week 1 | Team 1 | Threats focused | Sector 1: So. Matalangao, Brgy. Abaraoan, Roxas | 3
SEPTEMBER | Week 1 | Team 2 | Threats focused | Sector 2: So.Maraibo, Brgy. Antonino, Roxas | 3
SEPTEMBER | Week 1 | Team 3 | Threats focused | Sector 3: So. Pamuayan, Brgy. Port Barton, San Vicente | 3
SEPTEMBER | Week 1 | Team 4 | Threats focused | Sector 4: So. Manggahan, Brgy. Tanataon, Dumaran | 3
SEPTEMBER | Week 2 | Team 1 | Threats focused | Sector 1: So. Little Caramay, Brgy. Magara, Roxas | 3
SEPTEMBER | Week 2 | Team 2 | Threats focused | Sector 2: So. Maragok, Brgy. Antonino, Roxas | 3
SEPTEMBER | Week 2 | Team 3 | Threats focused | Sector 3: So. Decala, Brgy. Caruray, San Vicente | 3
SEPTEMBER | Week 2 | Team 4 | Threats focused | Sector 4: So. Lumiliba, Brgy. Capayas, Dumaran | 3
SEPTEMBER | Week 3 | Team 1 | Threats focused | Sector 1: So. Upper Marirong, Brgy. Nicanor Zabala, Roxas | 3
SEPTEMBER | Week 3 | Team 2 | Threats focused | Sector 2: So. Stockpile, Brgy. Dumarao, Roxas | 3
SEPTEMBER | Week 3 | Team 3 | Threats focused | Sector 3: So. JMP, Brgy. Alimanguan, San Vicente | 3
SEPTEMBER | Week 3 | Team 4 | Threats focused | Sector 4: So. Centro , Brgy. Magsaysay, Dumaran | 3
SEPTEMBER | Week 4 | Team 1 | Threats focused | Sector 1: So. Bayugon, Brgy. Tinitian, Roxas | 3
SEPTEMBER | Week 4 | Team 2 | Threats focused | Sector 2: So. Subingao, Brgy. Dumarao, Roxas | 3
SEPTEMBER | Week 4 | Team 3 | Threats focused | Sector 3: So. Tagpis and Bokbok, Brgy. San Isidro, San Vicente | 3
SEPTEMBER | Week 4 | Team 4 | Threats focused | Sector 4: So. Malaking Patag, Brgy. Sta. Maria, Dumaran | 3
|  |  |  | Total | 144
Notes
Patrolling includes preparatory activities such as coordinating with LGUs and other authorities, data syncing, preparing for responses
Consult map2 when doing this
Types of patrols: threats focused and indicator species-focused
If there are less than five teams, erase the extra number of teams in the matrix

## map2
Patrol map
Insert circles in the targeted patrol area for the entire planning period (quarter) for each team
Patrol map
Insert circles in the targeted patrol area for the entire planning period (quarter) for each team
Notes
Indicate in the map the planned routes
Legend
Sector 1
Sector 2
Sector 3
Sector 4
Sector 1
Poblacion-Brgy. Tinitian
26,060 ha
Sector 2
Poblacion-Brgy. Bagong Bayan
26,060 ha
Sector 3
San Vicente
39,090 ha
Sector 4
Araceli-Dumaran
39,090 ha